## Sheet1
Date | Discipline | Work Description | Reported Status | Estimated Progress
2026-09-08 | Civil | Foundation concreting for compressor unit started early shift. | In Progress | 40%
2026-09-09 | Civil | Compressor foundation concreting completed by 18:00 hrs. | Completed | 100%
2026-09-14 | Piping | Pipe rack erection ongoing with crane 50T. | In Progress | 60%
2026-09-17 | Piping | Suction line joint fit-up and alignment completed. | Completed | 100%
2026-09-18 | Electrical | Overhead cable tray installation started in compressor room. | Started | 20%