## Sheet1
activity_id | level | discipline | wbs_package | activity_description | planned_start | planned_finish | baseline_status
CIV-FND-001 | L5 | Civil | Foundation Works | Excavation for Compressor Foundation | 2026-09-01 | 2026-09-03 | PLANNED
CIV-FND-002 | L5 | Civil | Foundation Works | Plain Cement Concrete (PCC) for Compressor Foundation | 2026-09-04 | 2026-09-05 | PLANNED
CIV-FND-003 | L5 | Civil | Foundation Works | Reinforcement Work for Compressor Foundation | 2026-09-06 | 2026-09-09 | CRITICAL
CIV-FND-004 | L6 | Civil | Foundation Works | Foundation Concreting for Compressor Unit | 2026-09-10 | 2026-09-11 | CRITICAL
CIV-FND-005 | L6 | Civil | Foundation Works | Curing and Deshuttering of Compressor Foundation | 2026-09-12 | 2026-09-16 | PLANNED
ROT-EQP-001 | L5 | Mechanical | Rotating Equipment | Compressor Equipment Placement on Foundation | 2026-09-18 | 2026-09-20 | CRITICAL
ROT-EQP-002 | L6 | Mechanical | Rotating Equipment | Compressor Shaft Alignment and Grouting | 2026-09-21 | 2026-09-24 | PLANNED
PIP-ERE-001 | L5 | Piping | Pipe Rack | Pipe Rack Structural Steel Erection | 2026-09-12 | 2026-09-16 | PLANNED
PIP-ERE-002 | L6 | Piping | Pipe Rack | Piping Alignment and Joint Fit-Up | 2026-09-16 | 2026-09-19 | PLANNED
PIP-LIN-001 | L6 | Piping | Process Piping | Suction and Discharge Process Line Installation | 2026-09-20 | 2026-09-25 | CRITICAL
PIP-HYD-001 | L6 | Piping | Process Piping | Hydrotesting of Compressor Header Line | 2026-09-26 | 2026-09-28 | MILESTONE
ELE-CAB-001 | L5 | Electrical | Cabling and Trays | Main Overhead Cable Tray Installation | 2026-09-17 | 2026-09-20 | PLANNED
ELE-CAB-002 | L6 | Electrical | Cabling and Trays | HT Power Cable Pulling and Termination | 2026-09-21 | 2026-09-24 | PLANNED
ELE-MOT-001 | L6 | Electrical | Substation Works | Electric Motor Hookup and Insulation Resistance Test | 2026-09-25 | 2026-09-27 | PLANNED
INS-INS-001 | L5 | Instrumentation | Field Instruments | Pressure and Temperature Transmitter Installation | 2026-09-22 | 2026-09-25 | PLANNED
INS-TST-001 | L6 | Instrumentation | Loop Testing | Transmitter to PLC Instrument Loop Checking | 2026-09-26 | 2026-09-29 | CRITICAL
HSE-SAF-001 | L5 | HSE | Safety Systems | Fire Hydrant and Flame Detector Placement | 2026-09-18 | 2026-09-22 | PLANNED
HSE-INS-001 | L6 | HSE | Safety Systems | Emergency Safety Shower and Eyewash Inspection | 2026-09-24 | 2026-09-25 | PLANNED